## Product Backlog
ID | Group | Title | Description | Added on | Originator | Deadline | Estimation | Priority | Status | Sprint | Notes
1 |  | An item | Some description | 2014-10-10 |  | 2014-11-10 | 10 |  |  | 1
This is where you store your product backlog items. If you are following SCRUM by the book, the format to adopt are “user stories” (“as a ... I want ... because ...”). Here we are a bit more general in the structure of items, which have a title, can be assigned a group, and have a description. The deadline is another “odd” field if you are working with SCRUM. Still, if you use this template for managing your todos, it might be useful. All the rest is pretty much standard. See “Introduction to Software Project Management” (www.spmbook.com) for more information and material. This is version: 1.0 - released 2015.05 (C) 2015 Adolfo Villafiorita License: MIT (http://opensource.org/licenses/MIT) (but if you attribute the work, I appreciate)

## Sprints Specification
ID | Name | Planned Start Date | Duration (Days) | Planned End Date | Allocated Points | Actual Burndown | Burndown Difference
1 |  | 2014-10-12 | 10 | 2014-10-22 | 10
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
Formulas:
Planned End Date = [Planned Start Date]+[Duration (Days)]

## Burndown Template
Burndown Chart
| Sprint ID | 1
| Start Date | 2014-10-12
| Duration | 10
| End Date | 2014-10-22
| Allocated Points | 10
| Average Point Burndown | 1
| Actual Burndown | 0
| Remaining Points | 10
|  | Day > | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  | Date > | 2014-10-12 | 2014-10-13 | 2014-10-14 | 2014-10-15 | 2014-10-16 | 2014-10-17 | 2014-10-18 | 2014-10-19 | 2014-10-20 | 2014-10-21 | 2014-10-22 | 2014-10-23 | 2014-10-24 | 2014-10-25 | 2014-10-26 | 2014-10-27 | 2014-10-28 | 2014-10-29 | 2014-10-30 | 2014-10-31 | 2014-11-01 | 2014-11-02 | 2014-11-03 | 2014-11-04 | 2014-11-05 | 2014-11-06 | 2014-11-07 | 2014-11-08 | 2014-11-09 | 2014-11-10 | 2014-11-11
|  | Remaining Days > | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | -1 | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20
|  | Ideal burn-down > | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | -1 | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20
|  | Actual burn-down > | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task ID | Title | Allocated to / Remaining > | 0 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | -1 | -2 | -3 | -4 | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20
1 | 0 |  | 10
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
| #N/A |  | #N/A
Insert Task ID; the other information about a task is derived from the backlog. If you want you can also specify to whom a task is allocated
Insert here the Sprint ID (as found in Sprints Specification). All the other data is automatically inserted by looking at the sprint specification (including “date”, remaining days, etc.)

## Actual Speed
Item ID | Date | From Time | To Time | Hours | Burned | Speed | Notes
|  |  |  | 0 | 1 | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
|  |  |  | 0 |  | #DIV/0!
If you are interested in computing your velocity, you can use this sheet to log your time and points burned.